Budget Planning Checklist

The following costs must be taken into account when planning a special event:

1.  Facilities/Equipment

- Meeting/reception room rental

- Overnight accommodations

Rental of:

- Chairs

- Tables

- Props

- Lectern

- Tent

- Canopy

- Lighting

- Extra help

- Coat checkroom

- Electrical/telephone hookups

- Set-up charges

- Flooring/carpeting Risers

2.  Food Service

- Number of people to be served

Cost per person for:

- Luncheon

- Dinner

- Afternoon break

- Cocktail hour

- Liquor/wine

- Other beverages

- Table linen

- Gratuities

3. Decorations

- Flowers

- Table decorations

- Extra plants

- Corsages

- Boutonnieres

- Candles

- Directional signs

- Balloons

- Ribbon

4. Design & Printing

- Design fee

- Advance announcements

- Invitations

- Programs

- Promotional flyers

- Posters Tickets Maps

- Name tags

- Registration packets

5. Postage/Shipping

- Invitation & reply card postage

- Bulk mailing of promotional materials

- Mailing house charges

- Shipping

6. Recognition items

- Awards/plaques

- Engraving Calligraphy

7. Miscellaneous

- VIP travel/expenses

- Honoraria

- Gifts

- Mementos

- Extra help

- Security

- Insurance

- First-aid station

8. Transportation

- Buses

- Vans

- Parking

- Valets

9. Entertainment

- Fees

- Additional equipment

- Promoter fees

- Contract

10. Publicity

- Advertising

- Photographer

- Printed photos

- Slides

- Duplicating

- Mailing

- Hospitality for press room equipment

- Banners

11. Audio-Visual Equipment

- Slide/film projectors

- Screens

- Extension cords

- Microphones

- Speaker system

- VCRs & monitors

- Overhead projectors

- Flip charts

- Technician/operator service

12. Office Expenses

- Staff time

- Overtime/comp time

- Additional staff

- Data processing

- Phones

- Duplicating

- Supplies (pens, paper)

- Complimentary tickets

- Staff accommodations

- Staff travel/expenses

Successful Special Events Planning Timeline

Six months to a year ahead:

- Select a theme

- Select the date

- Clear the date with important participants

- Double-check for conflicts with major institution or city functions

- Consider whether weather conditions or other demands on people's time (summer vacations, the start of school, holidays) might make the date inconvenient

- Plan and obtain approval of a budget

- Create a preliminary guest list

- Select and reserve a facility

- Develop a rain plan if the event is outdoors

- Reserve a block of hotel rooms

- Select and order recognition items and get them engraved immediately

- Order favors, souvenirs

- Reserve special equipment (vans, busses, tables, chairs, tents)

- Confirm master of ceremonies and speakers

- Audition entertainers

- Plan audio-visual presentations

- Plan promotion and publicity

Three to six months ahead:

- Plan and get approval of invitations

- Finalize guest list

- Select menus

- Print tickets and parking permits

- Keep campus officials, deans, and administrative officers informed of your plans

- Plan decorations and color scheme

- Send advance announcements

Two months ahead:

- Address invitations and set a mailing date

- Finalize decorations and facility arrangements

- Make hotel and transportation arrangements for out-of-town dignitaries

- Secure hosts/hostesses to assist with the event

- Make directional and welcome signs

- Write and print program

- Inspect the facility

- Continue publicity on schedule

Two to four weeks ahead:

- Record and acknowledge RSVPs

- Stuff registration packets

- Send final instructions to all dignitaries

- Write speeches and introductions

- Create a sating chart

Two weeks ahead:

- Have final meetings with florist, caterer, entertainers, etc.

- Schedule delivery times for special equipment

- Work with public relations staff on final publicity arrangements

- Duplicate all speeches (in case someone forgets to bring their speech)

One week ahead:

- Print the guest list in alphabetical order

- Finish place cards

- Meet with hosts and hostesses

- Gather all awards/plaques

- Make catering guarantees

The big day:

- Arrive early

- Have all instructions, phone numbers, keys, etc. with you

- Check all facilities and grounds

- Assign one worker to be your assistant (to run errands, send messages, etc.)

- Relax and smile! All your planning will pay off!